## Sheet1
Tech stack (Next.js, React.js, Node.js, Express, MongoDB, Razorpay). Here’s a detailed plan:
### 1. **Single Product and Multi-Product Pages for Selling**
#### **Frontend (Next.js + React.js)**
- **Single Product Page:**
- Create a dynamic route in Next.js (e.g., `/product/[id]`).
- Use React components to display product details like images, description, pricing, reviews, and "Add to Cart" functionality.
- Integrate Razorpay for the payment gateway.
- **Multi-Product Page:**
- Create a products listing page (e.g., `/products`), which fetches a list of products from the backend using Next.js API routes.
- Filter, sort, and pagination options for a smooth user experience.
#### **Backend (Node.js + Express + MongoDB)**
- **API for Products:**
- Create APIs for CRUD operations on products (GET for listing products, POST for creating products, PUT for updating, DELETE for removing products).
- MongoDB will store product data (title, description, images, price, category, etc.).
- **Payment Gateway Integration:**
- Use Razorpay APIs to handle payment transactions.
- Backend logic will generate payment links or requests and handle payment success/failure callbacks.
#### **Timeline Estimate:**
- **2-3 Weeks** for full functionality, including front-end integration, product listing, and payment gateway setup.
### 2. **Video Content Uploads and Connections for Video Courses**
#### **Frontend (Next.js + React.js)**
- **Video Upload Page:**
- Create a form using React where users can upload video files (course material).
- Use services like AWS S3, Firebase Storage, or any CDN to store the video files.
- **Video Course Page:**
- Create a dynamic page that fetches and plays video courses using HTML5 video player or third-party libraries like Plyr or Video.js.
#### **Backend (Node.js + Express + MongoDB)**
- **API for Video Uploads:**
- Create an API to handle video uploads and store metadata (title, description, URL) in MongoDB.
- Use AWS SDK or Firebase Admin SDK for uploading videos to cloud storage.
- **Authentication & Authorization:**
- Ensure only authorized users (course creators or admins) can upload videos.
- Implement access control for viewing videos (e.g., only users who purchased the course).
#### **Timeline Estimate:**
- **2-3 Weeks** for setting up video uploads, storage, and integration with front-end.
### 3. **Event Creation**
#### **Frontend (Next.js + React.js)**
- **Event Creation Form:**
- Allow users to create events with fields like event name, date, description, location (if physical), and video link (if online).
- **Event Listings and Registration:**
- Display a list of upcoming events on the front-end.
- Allow users to register for events and save their registration info.
#### **Backend (Node.js + Express + MongoDB)**
- **Event Management API:**
- Create API endpoints to add, update, list, and delete events.
- Store event details in MongoDB.
- **Notifications and Reminders:**
- Integrate with email or SMS APIs (SendGrid, Twilio) to send reminders to registered users.
#### **Timeline Estimate:**
- **2 Weeks** for event creation, display, and user registration functionality.
### 4. **Custom Payment Page**
#### **Frontend (Next.js + React.js)**
- **Custom Checkout Pages:**
- Design custom checkout flows using React and Razorpay payment buttons.
- Include features like multiple payment methods (cards, UPI, wallets) and support for discount codes or offers.
#### **Backend (Node.js + Express + MongoDB)**
- **Payment API Integration:**
- Use Razorpay’s API to create orders, handle payment verifications, and store transaction details.
- Handle callbacks from Razorpay to update the status of payments (success, failure, pending).
#### **Timeline Estimate:**
- **1-2 Weeks** for integrating Razorpay and creating custom payment flows.
### 5. **Telegram Group Channel Creation**
#### **Frontend (Next.js + React.js)**
- **Telegram Integration:**
- Provide a simple UI for users to join Telegram groups or channels after purchasing a product or course.
- Use Telegram’s deep link or API to allow users to be added to specific channels.
#### **Backend (Node.js + Express)**
- **API for Group Management:**
- Use Telegram Bot API or Telegram's HTTP API to manage group/channel memberships.
- Once a user purchases a product, use the backend to automatically invite them to a specific group/channel.
#### **Timeline Estimate:**
- **1-2 Weeks** to handle Telegram group integration.
### **Complete Stack Breakdown**
- **Frontend:**
- **Next.js:** Framework for React with SSR (Server-Side Rendering) and static site generation.
- **React.js:** Component-based frontend library for building dynamic user interfaces.
- **Tailwind CSS/Material UI:** (Optional) for styling the frontend.
- **Backend:**
- **Node.js + Express:** Server-side framework to handle API requests, file uploads, authentication, and payment handling.
- **MongoDB:** Database to store product data, user details, events, and transaction information.
- **Razorpay:** For handling all payment-related processes.
- **AWS S3/Firebase Storage:** For storing video content (or any other cloud-based storage solution).
### **Project Timeline Overview**
- **Planning & Architecture:** 1 week
- **Single/Multi-product pages + Payment Integration:** 2-3 weeks
- **Video content upload & course handling:** 2-3 weeks
- **Event creation & management:** 2 weeks
- **Custom payment page setup:** 1-2 weeks
- **Telegram group integration:** 1-2 weeks
- **Testing and QA:** 1-2 weeks
### **Total Estimated Time:**
**9-13 weeks** depending on the complexity of features and thorough testing.
### **Approach:**
1. **Phase 1 (Core Features):**
- Set up the Next.js and React.js environment.
- Build product pages (single and multi-product) and integrate payment with Razorpay.
- Implement the backend for handling product data, payments, and basic authentication.
2. **Phase 2 (Video and Events):**
- Add the video content upload system.
- Build the event creation and management module.
3. **Phase 3 (Advanced Features):**
- Customize payment pages for specific products or services.
- Implement Telegram group/channel integration.
4. **Phase 4 (Testing and Deployment):**
- Conduct extensive testing (unit tests, integration tests).
- Deploy the application (consider platforms like Vercel for frontend and AWS/DigitalOcean for backend).
Let me know if you want further details or assistance with any specific part!